## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
3 | AKSHAYA SHERLA | 2026-02-05 | Code upload failed for large Python files | Sprint 1 | Self | Functional | Added file size validation and optimized upload handling | 2026-02-06 | Closed | Working correctly now
4 | AKSHAYA SHERLA | 2026-02-12 | Syntax errors were not detected in some edge cases | Sprint 2 | Self | Logical | Improved error detection logic and validation | 2026-02-14 | Closed | All edge cases tested
5 | AKSHAYA SHERLA | 2026-02-20 | Multiple file upload feature not working properly | Sprint 2 | Self | Functional | Updated file handling logic for multiple inputs | 2026-02-25 | Open | Still needs improvement
6 | AKSHAYA SHERLA | 2026-03-05 | AI suggestions not generating for some inputs | Sprint 3 | Self | Functional | Improved API handling and fallback responses | 2026-03-08 | Closed | Working fine after fix
7 | AKSHAYA SHERLA | 2026-03-15 | Incorrect score calculation for complex code | Sprint 3 | Self | Logical | Fixed scoring algorithm and added validations | 2026-03-18 | Closed | Accuracy improved
8 | AKSHAYA SHERLA | 2026-03-25 | Chatbot response delay issue | Sprint 4 | Self | Performance | Optimized response time and reduced delay | 2026-03-28 | Open | Needs further optimization
9 | AKSHAYA SHERLA | 2026-03-30 | UI alignment issues in dashboard | Sprint 4 | Self | UI | Fixed CSS alignment and layout issues | 2026-04-01 | Closed | UI looks proper now

## Sheet2
Logical
User Interface
Maintainability
Standards
Others